## Progress invoice
Your business name | [6 empty] | PROGRESS INVOICE
Street address, City, State/Province, ZIP
Phone ¦ Email ¦ License no., if any
Tax or business number, if any
BILL TO |  |  | PROJECT |  |  | Invoice no. | 1001
Owner or customer name |  |  | Project name |  |  | Progress billing no. | 3
Billing address |  |  | Job site address |  |  | Work up to | 2026-10-31
Phone or email |  |  | Contract no. and date |  |  | Invoice date | 2026-11-02
[6 empty] | Terms (days) | 30
Due date
ORIGINAL CONTRACT (schedule of values)
ITEM | DESCRIPTION OF WORK | SCHEDULED VALUE | PREV. % | % TO DATE | PREVIOUSLY BILLED | THIS PERIOD | COMPLETED TO DATE
1 | Demolition and site prep | 4000 | 100% | 100%
2 | Framing | 12000 | 50% | 100%
3 | Electrical rough-in | 6000 | 0% | 50%
4 | Plumbing rough-in | 5000 | 0% | 40%
5 | Drywall and finish | 8000 | 0% | 0%
6
7
8
9
10
Subtotal
APPROVED CHANGE ORDERS
ITEM | DESCRIPTION OF WORK | SCHEDULED VALUE | PREV. % | % TO DATE | PREVIOUSLY BILLED | THIS PERIOD | COMPLETED TO DATE
CO-1 | Add 6 pot lights in kitchen (signed Oct 14) | 1200 | 0% | 100%
CO-2
CO-3
CO-4
CO-5
Subtotal
SUMMARY
Original contract sum
Approved change orders
Revised contract sum
Work completed to date
Previously billed
Work this period
|  |  | Retainage rate (enter 0% if your contract has none) |  |  |  | 5%
Less retainage held on this period
Subtotal this invoice
|  |  | Tax rate (if tax applies to this work) |  |  |  | 0%
Tax
AMOUNT DUE THIS INVOICE
Retainage held to date (paid when the contract says)
Contract balance left to bill
NOTES
Percent complete is our measure of work in place up to the date above. Change orders are billed only once signed.
Payment is due by the due date above. How to pay: card link, bank transfer details, cheque payable to ...
Retainage, if any, is held under the contract terms and released when the contract says.
Signature: ______________________________ Date: ______________
Template from brickbyclick.ai. Delete this line if you like.

## T&M invoice
Your business name |  |  |  | INVOICE
Street address, City, State/Province, ZIP
Phone ¦ Email ¦ License no., if any
BILL TO |  |  | Invoice no. | 1001
Customer name |  |  | Invoice date | 2026-11-02
Billing address |  |  | Terms (days) | 14
JOB SITE |  |  | Due date
Job site address ¦ Project name
LABOUR (trade or worker) | HOURS | UNIT | RATE | AMOUNT
Carpenter | 16 | hr | 65
Labourer | 16 | hr | 40
Subtotal
MATERIALS | QTY | UNIT | UNIT PRICE | AMOUNT
2x6 studs, 8 ft | 40 | ea | 8.5
Drywall, 4x8 sheets | 30 | ea | 16
Fasteners and adhesive | 1 | lot | 85
Subtotal
EQUIPMENT, DISPOSAL AND PERMITS | QTY | UNIT | PRICE | AMOUNT
Dumpster, 20 yd | 1 | ea | 450
Subtotal
APPROVED CHANGE ORDERS | QTY | UNIT | PRICE | AMOUNT
CO-1: add outlet in hallway (signed Oct 20) | 1 | ea | 180
Subtotal
Labour
Materials
Equipment, disposal and permits
Change orders
Subtotal
| Tax rate |  |  | 5%
Tax
Total
| Deposit received |  |  | 1000
AMOUNT DUE
Payment is due by the due date above. How to pay: card link, bank transfer, cheque payable to ...
Template from brickbyclick.ai. Delete this line if you like.

## How to use
How to use this construction invoice template
Progress invoice tab: list the contract as a schedule of values (each part of the job and its price). Each billing period,
copy last period's "% to date" into "Prev. %", then type the new "% to date". The sheet works out what was billed before, what is billed this period and what is complete.
Change orders go in their own block, only once the customer has signed them. They add to the revised contract sum.
Retainage: only if your contract has it. Enter the rate from the contract (or 0%). The sheet holds that share of this period's work and shows the total held to date.
It assumes the same retainage rate every period. If your contract reduces it later, change the rate and check the figures.
Tax: whether tax applies, and to which part of the job, depends on where you work. Ask your accountant.
T&M invoice tab: for time-and-materials jobs. Labour hours, materials, equipment and change orders each subtotal, then tax, deposit and the amount due.
Type only in the description, quantity and price cells. Do not type in Amount or the summary cells.
Google Sheets: upload to Drive and open with Google Sheets. Excel: open and save a master copy. Send each invoice as a PDF.